## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
1 | - | Set up rough database | 1 | Setting up necessary environments for development |  |  |  | Kingsley - 100%
2 | - | Set up flask frame | [5 empty] | Connor - 100%
3 | - | Set up laravel framework | [5 empty] | Spencer - 100%
4 | - | Set up user acc |  | Set up user acc on Laravel |  |  |  | Spencer - 100%
5 | - | Create Logo and Banner | 2 | Set up Home Page |  |  |  | Sammy - 100%
6 | - | Create Full Mockup | [5 empty] | Kingsley - 100%
7 | - | Set up Front End | [5 empty] | Spencer - 100%
8 | - | Solidify Database |  | Setting up necessary environments for development |  |  |  | Spencer - 50%, Connor - 50%
9 | 1 | Set up Recipe Card | 3 | Setting up recipe addition/posting |  | 4 | 1 | Spencer 100%
10 |  | Set Up Recipe Addition |  |  |  |  | 1
11 | 1 | Updated Database |  | Setting up necessary environments for development |  |  |  | Connor - 100%
12 | 3 | Set up Search Function | 4 | Setting up environments for the recipe cards |  | 2 | 1 | Spencer 100%
13 | 3 | Set up Tags
14 | 3 | Create HTML Template | [5 empty] | Connor - 100%