## Sheet1
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
1 | As a college student with one roommate, I want to find cheap recipes with small portion sizes so that I can eat home cooked meals on a budget without always having leftovers. | 3 | M | W | 2
2 | As an experimental home chef, I want to get feedback on my recipes so that I can improve. | 5 | M | W | 2
3 | As somebody on a tight schedule, I want to find recipes that I can make quickly so that I can get on with my day. | 3 | L | W | 1
4 | As a poor planner, I want to find recipes I can make with the ingredients I have so that I don’t have to plan my meals in advance. | 6 | L | W | 3
5 | As somebody who cares about my health, I want to make sure I have nutrition facts about recipes I make so that I can eat healthier. | 4 | L | W | 2
6 | As a picky eater, I want to save recipes I like for later so I can make them again. | 4 | H | W | 3
7 | As a vegan, I want to find only recipes that fit my dietary needs so that I can save time. | 3 | L | W | 1
8 | As a professional chef, I want to see new and creative recipes so that I can keep trying new things. | 3 | M | W | 2
9 | As a professional chef, I want to share my recipes so I can share my work with others. | 2 | H | W | 4
10 | As somebody stranded at home from COVID, I want to find baked goods I can make with minimal ingredients so I can kill some time. | 3 | M | W | 2
11 | As a parent to a picky eater, I want creative ways to sneak vegetables into meals so I can make my kid eat healthier. | 4 | L | W | 2
12 | As an intense competitor, I want to see how my recipes ratings stack up against other similar ones to validate myself as a chef. | 5 | M | W | 4
13 | As somebody who recently lost their grandma, I want to share her recipes with the world to help keep her memory alive. | 2 | M | W | 2
14 | As a food company, I want to slip branded ingredients into recipes so I can sell more of my product. | 6 | M | W | 5
15 | As an adventurous eater, I want help finding the ingredients needed to make unfamiliar recipes so I can try foods that I wouldn’t normally come across. | 7 | M | W | 5
16 | As an exchange student, I want to find recipes from my home country so I can make myself comfort food. | 4 | L | W | 2
17 | As a fan of cooking shows, I want to find recipes from my favorite celebrity chefs so I can cook along with my favorite shows. | 9 | L | W | 2
18 | As a pet owner, I would like to find recipes so that I can put my pets on a raw diet or give them homemade treats. | 9 | L | W | 2
19 | As somebody with a birthday coming up, I would like to find recipes for different kinds of cakes so I can make some treats. | 9 | L | W | 1
20 | As somebody with a friend from a different culture, I would like to try to make a dish they’re familiar with so I can make them feel comfortable. | 4 | L | W | 2
21 | As a traveler, I would like to learn how to make dishes that I’ve tasted before so I can expand my repertoire. | 9 | M | W | 4
22 | As a mother or father, I would like to learn how to cook homemade meals for our family so we don’t have to eat out. | 10 | M | W | 3
23 | As someone who doesn’t have the time to cook everyday, I would like to find recipes that will give me leftovers so I can get more out of one meal. | 9 | L | W | 2
24 | As a child whose parents work a lot, I would like to find simple recipes that will teach me how to cook for myself so I can be somewhat self sufficient. | 8 | M | W | 3
25 | As an ER worker, I would like to find recipes for food that tastes ok warmed up so that it’s ok if I get interrupted mid meal. | 8 | L | W | 2
26 | As someone who packs lunches for others, I would like to find recipes that other users say will keep well throughout the day. | 10 | L | W | 1
27 | As someone who takes care of children, I would like to find recipes for healthy snacks so I can make the children treats. | 10 | L | W | 2
28 | As someone with an allergy or intolerance, I would like to find recipes that other people with my intolerance approve of so I know they will not upset my stomach. | 10 | M | W | 2
29 | As a meal planner, I want to save a list of recipes so I can plot out my meals for the week. | 8 | M | W | 6
30 | As a meal planner, I would like to make a shopping list of the ingredients I need to make recipes I’ve saved so I can get all my shopping for a week done in one trip. | 6 | M | W | 4
31 | As a grocery store, I would like to show ads for foods at my store based on what ingredients are on somebody’s shopping list so I can sell more food. | 7 | M | W | 6